[image: image1.wmf][image: image2.wmf]
May 27, 2005
To:

Concrete contractors
Re:
Chavez School Building Concrete and Walkways

Informational Notice
1.
Contractors shall be required to submit bid on the attached “Request for 
Quotation”.
2. 
Contractors shall be required to submit the attached Non-collusion 
Affidavit during bid time.
3. 
Successful Contractor shall be required to submit the attached 
Contractor’s Certificate regarding Workers Compensation after award of 
contract.

4. 
Successful Contractor shall be required to submit the attached Certificate 
of Compliance after award of contract.
5. 
The successful contractor shall be responsible for providing a concrete 
mix design for Architect’s approval prior to any placement of concrete.

6. 
The successful contractor shall be responsible for providing certified 
payroll reports at the time of invoicing for the project.
7.
Work to be completed in three phases. Phase I will encompass 24x40 
relocatable classroom concrete footing work and shall start on June 20, 
2005 and be completed on July 1, 2005.. Phase II will encompass 36x40 
relocatable classroom concrete footing work and shall start on July 18, 
2005 and be completed on August 5, 2005. Phase III will encompass 
concrete walkways and mow strips around portable classrooms and shall 
start on August 15, 2005 and be completed on August 19, 2005.
8.
The district will be responsible for soil grading and excavation and pad 
prep.

9.
Add 3” thick slurry slab at interior of footings for both relocatable buildings.

10.District shall be responsible for relocating existing relocatable classrooms. 
Includes utilities disconnection, tear down of relo, crane work, re-
installation of relo on new concrete footing and re-connection of utilities.

11.
The District will be responsible for landscaping, repairing and re-installing 
new irrigation systems.

Please direct any questions to myself at 661-631-5885.

Sincerely:

______________________________

Robert Van Tassel

Supervisor:
School Planning & Construction

vantasselr@bcsd.k12.ca.us

Facilities
Ruben Solis, Director

1501 Feliz Dr.

Bakersfield CA. 93307
� EMBED MS_ClipArt_Gallery  ���








Bakersfield City School District


School Planning & Construction




















_1007274439

